## WBS
工作分解结构 | [5 empty] | Okane-Memo
© 2017 by Vertex42.com
| 项目开始日期 | 2021-09-06 |  |  |  |  | Work Breakdown Structure
级别 | WBS | 项目描述 | 负责人 | 开始时间 | 结束时间 | 备注
1 | 1 | 启动阶段 | 徐越 | 2021-09-06 | 2021-09-15
2 | 1.1 | 召开项目启动会议 | 徐越 | 2021-09-06 | 2021-09-08
2 | 1.1.1 | 确定项目 | 徐越 | 2021-09-06 | 2021-09-07
2 | 1.1.2 | 选定项目经理 | 徐越 | 2021-09-07 | 2021-09-07
2 | 1.1.3 | 识别项目干系人 | 徐越 | 2021-09-08 | 2021-09-08
| 1.2 | 评估项目可行性 | 徐越 | 2021-09-08 | 2021-09-10
| 1.3 | 起草项目章程 | 詹熹 | 2021-09-08 | 2021-09-15
1 | 2 | 规划阶段 | 林敏怡 | 2021-09-20 | 2021-10-13
2 | 2.1 | 召开项目计划会议 | 林敏怡 | 2021-09-20 | 2021-09-23
3 | 2.1.1 | 创建团队契约 | 徐越 | 2021-09-21 | 2021-09-21
2 | 2.2 | 创建项目管理计划 | 徐越 | 2021-09-24 | 2021-10-14
3 | 2.2.1 | 项目范围管理 | 徐越 | 2021-09-24 | 2021-09-29
4 | 2.2.1.1 | 创建范围管理计划 | 徐越 | 2021-09-24 | 2021-09-27
4 | 2.2.1.2 | 创建项目范围说明 | 徐越 | 2021-09-27 | 2021-09-27
4 | 2.2.1.3 | 创建WBS | 徐越 | 2021-09-28 | 2021-09-30
4 | 2.2.1.4 | 创建WBS词典 | 詹熹 | 2021-09-28 | 2021-09-30
3 | 2.2.2 | 项目进度管理 | 徐越 | 2021-10-01 | 2021-10-06
4 | 2.2.2.1 | 创建进度管理计划 | 徐越 | 2021-10-01 | 2021-10-04
4 | 2.2.2.2 | 创建里程碑 | 徐越 | 2021-10-04 | 2021-10-05
4 | 2.2.2.3 | 创建项目甘特图 | 徐越 | 2021-10-04 | 2021-10-06
4 | 2.2.2.4 | 进行功能点分析 | 詹熹 | 2021-10-05 | 2021-10-06
3 | 2.2.3 | 创建成本管理计划 | 詹熹 | 2021-10-07 | 2021-10-10
3 | 2.2.4 | 创建质量管理计划 | 林敏怡 | 2021-09-24 | 2021-09-28
3 | 2.2.5 | 创建风险管理计划 | 林敏怡 | 2021-10-07 | 2021-10-11
3 | 2.2.6 | 创建沟通管理计划 | 林敏怡 | 2021-10-12 | 2021-10-14
3 | 2.2.7 | 创建项目干系人管理计划 | 徐越 | 2021-10-11 | 2021-10-11
3 | 2.2.8 | 创建人力资源管理计划 | 徐越 | 2021-10-11 | 2021-10-13
1 | 3 | 执行阶段 | 林敏怡 | 2021-10-11 | 2021-11-17
2 | 3.1 | 分析 | 徐越 | 2021-10-11 | 2021-10-18
3 | 3.1.1 | 开展需求分析 | 徐越 | 2021-10-11 | 2021-10-14
4 | 3.1.1.1 | 创建用例模型 | 徐越 | 2021-10-15 | 2021-10-18
4 | 3.1.1.2 | 创建需求管理计划 | 徐越 | 2021-10-15 | 2021-10-15
2 | 3.2 | 设计 | 徐越 | 2021-10-19 | 2021-11-03
3 | 3.2.1 | 设计软件原型 | 詹熹 | 2021-10-19 | 2021-10-26
4 | 3.2.1.1 | 设计图标 | 徐越 | 2021-10-19 | 2021-10-21
4 | 3.2.1.2 | 设计界面 | 詹熹 | 2021-10-20 | 2021-10-26
2 | 3.2.2 | 数据库设计 | 林敏怡 | 2021-10-20 | 2021-10-22
3 | 3.2.2.1 | 绘制ER图 | 林敏怡 | 2021-10-21 | 2021-10-21
3 | 3.2.2.2 | 数据库表设计 | 林敏怡 | 2021-10-22 | 2021-10-22
3 | 3.2.2.3 | 编写数据字典 | 林敏怡 | 2021-10-22 | 2021-10-26
2 | 3.3 | 编码 | 詹熹 | 2021-10-27 | 2021-11-17
3 | 3.3.1 | 进行界面编码 | 林敏怡 | 2021-10-27 | 2021-11-01
3 | 3.3.2 | 完成数据库操作编码 | 詹熹 | 2021-11-02 | 2021-11-04
3 | 3.3.3 | 实现记账功能 | 徐越 | 2021-11-05 | 2021-11-08
3 | 3.3.4 | 实现图表功能 | 詹熹 | 2021-11-08 | 2021-11-12
3 | 3.3.5 | 实现数据同步功能 | 詹熹 | 2021-11-12 | 2021-11-17
1 | 4 | 收尾阶段 | 詹熹 | 2021-11-18 | 2021-11-26
2 | 4.1 | 编写用户操作手册 | 詹熹 | 2021-11-18 | 2021-11-18
2 | 4.2 | 编写项目最终报告 | 詹熹 | 2021-11-19 | 2021-11-22
2 | 4.3 | 项目经验总结 | 詹熹 | 2021-11-19 | 2021-11-22

## Help
HELP
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html |  | © 2017 Vertex42 LLC
About this Template
This template provides a very basic WBS table that you can use for defining a hierarchical work breakdown structure for a project plan or process.
Want more features and automation?
Try the Gantt Chart Template by Vertex42.com
Note: The formula for the WBS numbering was developed by Vertex42.com for the Gantt Chart Template Pro spreadsheet, and is copyrighted. See the terms of use.
Instructions
1) | Choose a Level from the drop-down list in column B. The WBS code is created automatically. When adding rows, you will need to copy the formula in the WBS code column into the newly added rows.
2) | Indent Task Descriptions using the Indent buttons in the Home tab.
3) | Add or hide columns as needed.
4) | A conditional formatting rule automatically highlights level 1 tasks. Go to Home > Conditional Formatting > Manage Rules to remove or edit this rule.
Terms of Use
See the following page for information about how you may use this spreadsheet.
https://www.vertex42.com/licensing/EULA_privateuse.html
REFERENCES
SEE ALSO | Vertex42.com: Gantt Chart Template
SEE ALSO | Vertex42.com: Project Management Templates
TIPS | Vertex42.com: Spreadsheet Tips Workbook

## ©
Work Breakdown Structure
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/work-breakdown-structure.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.